## Slide 1
SoLID DAQ preRD tasks and remaining work
Alexandre Camsonne
Data acquisition working group
Hall A Jefferson Laboratory
Data Acquisition
Jefferson Lab SoLID Pre-R&D Review
August 7th, 2020

## Slide 2: Outline
GANTT chart task
Man power
Spending
Impact of COVID
Conclusions

## Slide 3: GANTT chart

## Slide 4: Manpower
 | Month electronics engineer | Months DAQ staff | Physics staff | Postdoc |  |  |  |  |  |  | 
Tasks |  |  |  |  | 2020 | 2021 | 2020 | 2021 |  |  | 
Ecal trigger | 1 | 1 | 0.5 | 1 | 1 |  | Scott |  |  |  | 
GEM performance | 3 | 1 | 0.5 | 1 | 1 |  | UVA |  |  |  | 
GEM X-ray test | 0 | 0 | 0.5 | 1 | 0 | 1 | UVA |  |  |  | 
VMM setup | 1 | 1 | 0.5 | 1 |  | 1 |  | UVA |  |  | 
FADC VXS readout | 3 | 1 | 1 | 1 | 1 |  | Hanjie |  |  |  | 
FADC performance | 3 | 1 | 0.5 | 3 | 2 | 1 | Hanjie |  |  |  | 
Data transfer silo | 0 | 1 | 0.5 | 1 | 0 | 1 | Scott |  |  | 2020 | 2021
Cerenkov readout | 5 | 1 | 0.5 | 2 | 0 | 2 | Hall A postdoc |  | Hanjie | 3 | 5
PVDIS trigger prototype | 2 | 1 | 0.5 | 2 | 0 | 2 | Scott |  | UVA | 5 | 1
Data reduction algorithm | 6 | 3 | 0.5 | 3 | 1 | 2 | UVA |  | Scott | 6 | 
L3 farm need evaluation | 0 | 1 | 0.5 | 2 | 2 |  | Scott |  | Hall A postdoc | 2 | 4
Test stand - beam test | 1 | 1 | 0.5 | 2 |  | 2 |  | Hanjie |  |  | 
Deadtime for PVDIS | 3 | 2 | 1 | 3 |  | 3 |  | Hanjie |  | 16 | 10
SIDIS trigger prototype | 2 | 1 | 0.5 | 2 |  | 2 |  | Hall A postdoc |  |  | 
MRPC readout | 6 | 3 | 0.5 | 1 |  | 1 |  | Hall A postdoc |  |  | 
SPD readout and test | 3 | 1 | 0.5 | 1 |  | 1 |  | Hall A postdoc |  |  | 
Total months | 39 | 20 | 9 | 27 | 8 | 19 |  |  |  |  | 

## Slide 5: Spending profile

## Slide 6: Impact of COVID
Activities at the lab were stopped on March 23rd
Only work at home
Only essential personal at the lab
Delayed development and test stands by about 3 months

## Slide 7: Conclusion
Long lead items ordered
Man power identified
some delay with UVA rehitring a new postdoc
UMASS DAQ test stand being set up
VMM3 protype board on going for test with high rate
FADC Fast readout ongoing will be reused for fast APV25 readout with VTP
About 3 months delay due to COVID